## Task Management
BCS07 - Group 09 | CYBER ELEARNING
Requirements: https://apicrm.cybersoft.edu.vn/files/14-09-2022-02-12-43-duancuoikhoa-bc.pdf
Deploy Link: https://bcs-07-final-g9-e-learning.vercel.app/
Youtube Demo: https://www.youtube.com/watch?v=jRO5sl8GAvI&ab_channel=NewbieDevHuynh
Team member
1 | Huỳnh Quang Bảo
2 | Nguyễn Đình Anh Hào
3 | Đặng Thùy Linh
# The page will be built in Vietnamese as the main language and all APIs in the database will use "GP09" as the group code
Side | Components / Features | API | Start Date | Finish Date | % Completion | Assigned Member | Notes
| Setup and Self-research |  | 01/08/2023 - 10/08/2023 |  |  | All
USER | Trang Chủ
| Header / Footer | None | 2023-08-13 | 2023-08-13 | 100% | Huỳnh Quang Bảo
| Banner | None | 2023-08-14 | 2023-08-14 | 100% | Huỳnh Quang Bảo
| Achievement | None | 2023-08-14 | 2023-08-14 | 100% | Huỳnh Quang Bảo
| Course List | /api/QuanLyKhoaHoc/LayDanhSachKhoaHoc?tenKhoaHoc=${tenKhoaHoc}&MaNhom=${maNhom} | 2023-08-15 | 2023-08-15 | 100% | Huỳnh Quang Bảo
| Count Up Number | None | 2023-08-15 | 2023-08-15 | 100% | Huỳnh Quang Bảo
| Teacher Carousel | None | 2023-08-15 | 2023-08-15 | 100% | Huỳnh Quang Bảo
| Feedback From User | None | 2023-08-15 | 2023-08-15 | 100% | Huỳnh Quang Bảo
| Back-to-top Button | None | 2023-08-15 | 2023-08-15 | 100% | Huỳnh Quang Bảo
USER | Tìm Kiếm
| Search Bar on Header | None | 2023-08-17 | 2023-08-17 | 100% | Huỳnh Quang Bảo
| Search Bar in Collapsed Menu | None | 2023-08-17 | 2023-08-17 | 100% | Huỳnh Quang Bảo
| Left-side Filter | None | 2023-08-17 | 2023-08-17 | 100% | Huỳnh Quang Bảo
| Searched Courses | /api/QuanLyKhoaHoc/LayDanhSachKhoaHoc_PhanTrang?tenKhoaHoc=${tenKhoaHoc}&page=${page}&pageSize=${pageSize}&MaNhom=${maNhom} | 2023-08-17 | 2023-08-17 | 100% | Huỳnh Quang Bảo
USER | Đăng nhập - Đăng ký
| Login | /api/QuanLyNguoiDung/DangNhap | 2023-08-18 | 2023-08-19 | 100% | Huỳnh Quang Bảo
| Register | /api/QuanLyNguoiDung/DangKy | 2023-08-19 | 2023-08-20 | 100% | Huỳnh Quang Bảo
USER | Thông tin người dùng
| Layout - Personal Details | none | 2023-08-21 | 2023-08-21 | 100% | Huỳnh Quang Bảo
| Update Personal Details | /api/QuanLyNguoiDung/CapNhatThongTinNguoiDung | 2023-08-21 | 2023-08-22 | 100% | Huỳnh Quang Bảo
| Layout - Registerd Courses | none | 2023-08-23 | 2023-08-23 | 100% | Huỳnh Quang Bảo
| View All Registered Courses Search Courses | /api/QuanLyNguoiDung/ThongTinTaiKhoan | 2023-08-23 | 2023-08-24 | 100% | Huỳnh Quang Bảo
USER | Thông tin / Giới thiệu
| layout - Intro | None | 2023-08-25 | 2023-08-26 | 100% | Nguyễn Đình Anh Hào
| Update reponsive Intro | None | 2023-08-26 | 2023-08-28 | 100% | Nguyễn Đình Anh Hào
USER | Danh mục
| layout-Category | None | 2023-08-28 | 2023-08-29 | 100% | Nguyễn Đình Anh Hào
| reposive-Category | None | 2023-08-29 | 2023-08-29 | 100% | Nguyễn Đình Anh Hào
| courseCard-Category | /api/QuanLyKhoaHoc/LayKhoaHocTheoDanhMuc | 2023-08-29 | 2023-08-29 | 100% | Nguyễn Đình Anh Hào
USER | Khóa học
| layout course | None | 2023-08-26 | 2023-08-28 | 100% | Nguyễn Đình Anh Hào
| reposive course | None | 2023-08-28 | 2023-08-28 | 100% | Nguyễn Đình Anh Hào
| course card | /api/QuanLyKhoaHoc/LayDanhSachKhoaHoc | 2023-08-28 | 2023-08-28 | 100% | Nguyễn Đình Anh Hào
USER | Chi tiết khóa học
| Layout - Detail Page | None | 2023-08-28 | 2023-08-28 | 100% | Đặng Thùy Linh
| Get Course Information Fetch data into layout | /api/QuanLyKhoaHoc/LayThongTinKhoaHoc?maKhoaHoc=${maKhoaHoc} /api/QuanLyKhoaHoc/LayDanhSachKhoaHoc?tenKhoaHoc=${tenKhoaHoc}&MaNhom=${maNhom} | 2023-08-28 | 2023-08-28 | 100% | Đặng Thùy Linh
| Register Course | /api/QuanLyKhoaHoc/DangKyKhoaHoc | 2023-08-29 | 2023-08-29 | 100% | Đặng Thùy Linh
| Layout Responsive | None | 2023-08-29 | 2023-08-29 | 100% | Đặng Thùy Linh
USER | Blog
| Blog | None | 2023-08-19 | 2023-08-24 | 100% | Đặng Thùy Linh
| BlogContent | None | 2023-08-19 | 2023-08-24 | 100% | Đặng Thùy Linh
| BlogItem | None | 2023-08-19 | 2023-08-24 | 100% | Đặng Thùy Linh
| Blog SCSS | None | 2023-08-19 | 2023-08-24 | 100% | Đặng Thùy Linh
USER | Sự kiện
| Event | None | 2023-08-26 | 2023-06-27 | 100% | Đặng Thùy Linh
| EventContent | None | 2023-06-27 | 2023-06-27 | 100% | Đặng Thùy Linh
| EventSlide | None | 2023-06-27 | 2023-06-27 | 100% | Đặng Thùy Linh
| Sponsors | None | 2023-06-27 | 2023-06-27 | 100% | Đặng Thùy Linh
ADMIN | Quản lý người dùng
| Admin Layout Template User Management Template | none | 2023-08-25 | 2023-08-25 | 100% | Huỳnh Quang Bảo
| Admin Login Page | /api/QuanLyNguoiDung/DangNhap | 2023-08-25 | 2023-08-25 | 100% | Huỳnh Quang Bảo
| View All Users Add New Users Search Users | /api/QuanLyNguoiDung/LayDanhSachNguoiDung?MaNhom=${maNhom} /api/QuanLyNguoiDung/ThemNguoiDung /api/QuanLyNguoiDung/TimKiemNguoiDung?MaNhom=${maNhom}&tuKhoa=${tuKhoa} | 2023-08-26 | 2023-08-26 | 100% | Huỳnh Quang Bảo
| Update Users Delete Users | /api/QuanLyNguoiDung/CapNhatThongTinNguoiDung /api/QuanLyNguoiDung/XoaNguoiDung?TaiKhoan=${taiKhoan} | 2023-08-27 | 2023-08-28 | 100% | Huỳnh Quang Bảo
ADMIN | Quản lý khóa học
| Course Management Template | None | 2023-08-28 | 2023-08-28 | 100% | Huỳnh Quang Bảo
| View, Search, Delete Courses | /api/QuanLyKhoaHoc/LayDanhSachKhoaHoc?tenKhoaHoc=${tenKhoaHoc}&MaNhom=${maNhom} /api/QuanLyKhoaHoc/XoaKhoaHoc?MaKhoaHoc=${maKhoaHoc} | 2023-08-28 | 2023-08-28 | 100% | Huỳnh Quang Bảo
| Add New Courses | /api/QuanLyKhoaHoc/ThemKhoaHoc /api/QuanLyKhoaHoc/UploadHinhAnhKhoaHoc | 2023-08-29 | 2023-08-29 | 100% | Huỳnh Quang Bảo
| Update Courses | /api/QuanLyKhoaHoc/CapNhatKhoaHoc /api/QuanLyKhoaHoc/UploadHinhAnhKhoaHoc | 2023-08-29 | 2023-08-30 | 90% | Huỳnh Quang Bảo | Still have some problems with uploading images